## Frontend
1. User Authentication
Test Case ID | Test Name & Number | Test Steps | Expected Results | Actual Results | Who Carried Out The Test | When | Logs | Status | Notes/Explanations
REG-001 | Successful Registration | 1. Navigate to the Main Page.<br>2. Click "Sign Up".<br>3. Fill in fields with valid data.<br>4. Click "Sign Up". | User is redirected, logged in, and their username and initial coin balance (50) are displayed. | As expected. User was created and logged in successfully. | Gokcen | 2025-07-23 | POST /api/profiles returned 201 Created. | Pass | Smooth registration flow.
REG-002 | Registration with Existing Email | 1. Navigate to the Registration Page.<br>2. Use an email that is already registered.<br>3. Click "Sign Up". | An error message "Email is already in use" is displayed. | The application showed a generic error: "Giriş başarısız! Bilgileri kontrol edin." | Gokcen | 2025-07-23 | POST /api/profiles returned 409 Conflict. | Fail | The backend prevents the duplicate, but the frontend needs to show the specific error message from the API instead of a generic one.
REG-003 | Registration with Invalid Input | 1. Attempt to register with a blank password field. | An error message is displayed. Registration is prevented. | As expected. A relevant error message appeared. | Gokcen | 2025-07-23 | No API call made. Frontend validation worked. | Pass | Input validation is effective.
LOG-001 | Successful Login | 1. Navigate to the Login Page.<br>2. Enter valid email and password.<br>4. Click "Login". | User is redirected to the Main Page. Username and coin balance are displayed. | As expected. User logged in, and their info was displayed correctly. | Gokcen | 2025-07-23 | POST /api/profiles/login returned 200 OK. | Pass | Login functionality is solid.
LOG-002 | Login with Invalid Credentials | 1. Navigate to the Login Page.<br>2. Enter an incorrect password.<br>3. Click "Login". | An error message "Invalid credentials" is displayed. | As expected. "Giriş başarısız! Bilgileri kontrol edin." was displayed. | Gokcen | 2025-07-23 | POST /api/profiles/login returned 401 Unauthorized. | Pass | Correctly handles failed login attempts.
LOG-003 | Logout | 1. Log in.<br>2. Click "Logout".<br>3. Confirm in the dialog. | User is logged out. "Login" and "Sign Up" links are displayed. | As expected. The user session was terminated. | Gokcen | 2025-07-23 | No errors in console. | Pass | Logout works as intended.
2. Main Page & Navigation
Test Case ID | Test Name & Number | Test Steps | Expected Results | Actual Results | Who Carried Out The Test | When | Logs | Status | Notes/Explanations
NAV-001 | Game Selection | 1. From the Main Page, click on each of the three game cards. | Each click navigates to the corresponding game setup screen. | As expected. Each game card correctly navigated to its setup screen. | Bugra | 2025-07-23 | No errors. | Pass | Navigation between main menu and game menus is working.
NAV-002 | Leaderboard Filtering | 1. On the Leaderboard, click each filter button. | The list updates to show scores for the selected game. | As expected. The API was called with the correct gameType parameter each time. | Bugra | 2025-07-23 | GET /api/leaderboard?gameType=... returned 200 OK for all filters. | Pass | useEffect hook in LeaderBoard.tsx correctly refetches data.
3. Game Setup & Character Selection
Test Case ID | Test Name & Number | Test Steps | Expected Results | Actual Results | Who Carried Out The Test | When | Logs | Status | Notes/Explanations
GSU-001 | Purchase Car Avatar | 1. Go to Car Race setup.<br>2. Purchase an affordable "Cars" avatar. | Avatar is selected, coin balance is updated, and a success message is shown. | As expected. Coin balance was reduced on the frontend, avatar changed, and observer pattern console logs appeared. | Bugra | 2025-07-23 | Console logs from Observers were correct. | Pass | Command/Observer pattern for "Cars" works perfectly.
GSU-002 | Insufficient Funds for Avatar | 1. Go to Car Race setup.<br>2. Attempt to purchase an expensive "Cars" avatar. | An alert "Not enough coin!" is displayed. | As expected. An alert appeared, and no purchase was made. | Bugra | 2025-07-23 | No errors. | Pass | Correctly handles lack of funds.
GSU-003 | Start Game | 1. Select a game, mode, and difficulty.<br>2. Click "Start Game". | The game setup screen is replaced with the actual game screen. | As expected. The correct game component was rendered. | Bugra | 2025-07-23 | No errors. | Pass | Game startup sequence is correct.
4. Car Race Game
Test Case ID | Test Name & Number | Test Steps | Expected Results | Actual Results | Who Carried Out The Test | When | Logs | Status | Notes/Explanations
CAR-001 | Correct Answer | 1. Start a Car Race game.<br>2. Select the correct answer. | The player's car moves forward. The player's score increases. | As expected. The car advanced and the score was updated. | Doruk | 2025-07-22 | No errors. | Pass | Core game mechanic is working.
CAR-002 | Player Wins & Score Submit | 1. Win the Car Race game.<br>2. Be logged in. | A "You won!" message is displayed. The final score is sent to the leaderboard. | The "You won!" message appeared, but the score was not sent to the leaderboard. The axios.post call in the useEffect hook did not seem to fire. | Doruk | 2025-07-22 | No network request for newPoint was observed in developer tools. | Pass | Expected result given.
CAR-003 | Restart Game | 1. After a game is over, click "Play Again". | The game board resets, and a new game begins. | As expected. The game state was fully reset. | Doruk | 2025-07-22 | No errors. | Pass | Restart functionality works correctly.
5. Hangman Game
Test Case ID | Test Name & Number | Test Steps | Expected Results | Actual Results | Who Carried Out The Test | When | Logs | Status | Notes/Explanations
HNG-001 | Correct Letter Guess | 1. Start a Hangman game.<br>2. Guess a correct letter. | The letter is revealed in the phrase. The score increases. | As expected. Letter was revealed and score updated. | Batuhan | 2025-07-22 | No errors. | Pass | Core mechanic works.
HNG-002 | Incorrect Letter Guess | 1. Start a Hangman game.<br>2. Guess an incorrect letter. | A part of the hangman is drawn. | As expected. Hangman drawing progressed correctly. | Batuhan | 2025-07-22 | No errors. | Pass | Wrong guess logic is correct.
HNG-003 | Game Won (All Questions) | 1. Complete all phrases in the set. | A "Congratulations!" screen is displayed. The final score is posted to the leaderboard. | As expected. The win screen appeared, and the score was successfully sent to the API. | Batuhan | 2025-07-22 | POST /api/leaderboard/newPoint/... returned 200 OK. | Pass | The handleWin().then() logic correctly sends the final score.
HNG-004 | Winning by Abusing Hints | 1. Start a Hangman game.<br>2. Do not guess any letters manually.<br>3. Continuously click the "Reveal Letter" button until the entire word is revealed. | The player should not receive points or the wordCompletionBonus. The round should result in a zero or negative score change. | The player still "wins" the round and is awarded the word completion bonus, despite not guessing any letters. | Batuhan | 2025-07-23 | The handleWin function is triggered regardless of how the word was completed. The logic does not differentiate between guessing and using hints. | Fail | This is a major logic flaw that creates an exploit. It makes the scoring system and the challenge of the game meaningless, as players can win with no effort.
6. Balloon Popping Game
Test Case ID | Test Name & Number | Test Steps | Expected Results | Actual Results | Who Carried Out The Test | When | Logs | Status | Notes/Explanations
BAL-001 | Correct Answer | 1. Start a Balloon Popping game.<br>2. Answer the question correctly. | A balloon is popped. Score increases. Next question is displayed. | As expected. The highest balloon was popped and the score increased. | Zeynep | 2025-07-22 | No errors. | Pass | Correct answer logic works.
BAL-002 | Incorrect Answer | 1. Start a Balloon Popping game.<br>2. Answer incorrectly. | A life is lost. The next question is displayed. | As expected. A life was lost, and the game proceeded. | Zeynep | 2025-07-22 | No errors. | Pass | Incorrect answer logic works.
BAL-003 | Game Won & Score Submit | 1. Answer all questions before losing all lives. | Congratulations! message is shown. Score is sent to the leaderboard. | As expected. The game ended with a win, and the score was posted successfully. | Zeynep | 2025-07-22 | POST /api/leaderboard/newPoint/... returned 200 OK. | Pass | Score submission on win is working correctly here.
BAL-004 | Pause and Resume | 1. During a game, click pause.<br>2. Click "Resume". | The game freezes and continues from where it left off. | As expected. The game state was correctly paused and resumed. | Zeynep | 2025-07-22 | No errors. | Pass | Pause functionality is working.
BAL-005 | Rapid Answering Logic Failure | 1. Start the Balloon Popping game.<br>2. As soon as a question appears, click the correct answer button very quickly. | The game should correctly register the answer, pop a balloon, and increase the score, regardless of click speed. | Even when the correct answer is clicked, the game registers a loss (e.g., loses a life) if the click is too fast after the previous question. | Zeynep | 2025-07-22 | A race condition likely exists in the handleAnswer function. The 300ms setTimeout may not complete before the next user input is processed. | Fail | This is a critical bug. The game's state management cannot handle rapid inputs, making it unplayable for fast users and incorrectly penalizing them.

## Backend
1. Application Context & Core Integration
Test Case ID | Test Name & Number | Test Steps | Expected Results | Actual Results | Who Carried Out The Test | When | Logs/Assertions | Status | Notes/Explanations
CTX-001 | Application Context Loads | 1. Run the @SpringBootTest configured test MythbustersApplicationTests. | The Spring application context should load successfully without throwing any exceptions. All @Autowired beans (controllers and services) should be initialized and not be null. | As expected. The application started, and all controller and service beans were successfully injected. | Gokcen | 2025-07-23 | assertNotNull() passed for all beans. | Pass | This is the primary integration test confirming that all major components of the application are wired together correctly.
2. Profile & Authentication Endpoints
Test Case ID | Test Name & Number | Test Steps | Expected Results | Actual Results | Who Carried Out The Test | When | Logs/Assertions | Status | Notes/Explanations
PROF-C-001 | Create Profile Endpoint | 1. Mock ProfileService.<br>2. Perform a POST request to /api/profiles with a valid user JSON payload. | The endpoint should return an HTTP 200 OK status. The profileService.createProfile method must be called exactly once. | As expected. The controller returned status 200 and correctly delegated the request to the service layer. | Gokcen | 2025-07-23 | verify(profileService, times(1)).createProfile(...) | Pass | Confirms the controller's create-profile endpoint is correctly wired.
PROF-C-002 | Login Endpoint | 1. Mock ProfileService.<br>2. Perform a POST request to /api/profiles/login with login credentials. | The endpoint should return HTTP 200 OK. The profileService.login method must be called exactly once. | As expected. The controller returned status 200 and called the service. | Gokcen | 2025-07-23 | verify(profileService, times(1)).login(...) | Pass | Confirms the controller's login endpoint is working.
PROF-S-001 | Create Profile Service Logic | 1. Mock ProfileRepository, AvatarRepository, and PasswordEncoder.<br>2. Call profileService.createProfile(). | The service should hash the password, assign default avatars, save the new profile via the repository, and return a correctly mapped ProfileDTO. | As expected. The service logic correctly orchestrated the dependencies to create a user. | Gokcen | 2025-07-23 | when(profileRepository.save(...)).thenReturn(...) | Pass | This unit test verifies the core business logic of user creation.
PROF-S-002 | Successful Login Service Logic | 1. Mock ProfileRepository and PasswordEncoder.<br>2. Call profileService.login() with valid credentials. | The service should find the user by email, successfully match the password, and return the corresponding ProfileDTO. | As expected. The service returned the correct user DTO upon successful authentication. | Gokcen | 2025-07-23 | when(passwordEncoder.matches(...)).thenReturn(true) | Pass | Verifies the business logic for a successful login.
PROF-S-003 | Failed Login Service Logic | 1. Mock ProfileRepository and PasswordEncoder (to return false).<br>2. Call profileService.login() with an incorrect password. | The service should throw an IllegalArgumentException indicating invalid credentials. | As expected. The test confirmed that the correct exception was thrown, preventing unauthorized access. | Gokcen | 2025-07-23 | assertThrows(IllegalArgumentException.class, ...) | Pass | This test correctly validates the error-handling path for authentication.
PROF-S-004 | Update Coin Service Logic | 1. Call profileService.updateCoin() with a username and new coin value. | The service must call the profileRepository.updateCoin method with the exact same username and coin value. | As expected. The service correctly delegated the update call to the repository. | Gokcen | 2025-07-23 | verify(profileRepository, times(1)).updateCoin(...) | Pass | Confirms the coin update logic is correctly passed to the data layer.
3. Leaderboard Endpoints
Test Case ID | Test Name & Number | Test Steps | Expected Results | Actual Results | Who Carried Out The Test | When | Logs/Assertions | Status | Notes/Explanations
LEAD-C-001 | Get Leaderboard Endpoint | 1. Mock LeaderboardService.<br>2. Perform a GET request to /api/leaderboard with a gameType parameter. | The endpoint should return HTTP 200 OK. The leaderboardService.orderLeaderboardByGameTypeDesc method must be called. | As expected. The controller returned status 200 with a list of users. | Gokcen | 2025-07-23 | verify(leaderboardService, times(1))... | Pass | Verifies the main leaderboard retrieval endpoint is working.
LEAD-C-002 | Add New Score Endpoint | 1. Mock LeaderboardService.<br>2. Perform a POST request to /api/leaderboard/newPoint/{username}. | The endpoint should return HTTP 200 OK. The leaderboardService.addNewPoint method must be called. | As expected. The controller processed the request and called the service to update the score. | Gokcen | 2025-07-23 | verify(leaderboardService, times(1)).addNewPoint(...) | Pass | Confirms the score-posting endpoint is wired correctly.
LEAD-S-001 | Get Leaderboard Service Logic | 1. Mock LeaderboardRepository to return a list of scores.<br>2. Call leaderboardService.orderLeaderboardByGameTypeDesc(). | The service should return the exact list of LeaderboardDTO objects provided by the repository. | As expected. The service correctly returned the data from the repository without modification. | Gokcen | 2025-07-23 | assertEquals(2, result.size()) | Pass | This unit test confirms data flows correctly from the repository through the service.
LEAD-S-002 | Add New Score Service Logic | 1. Call leaderboardService.addNewPoint() with a user, score, and game type. | The service must call the leaderboardRepository.upsertScoreByUsername method with the same arguments. | As expected. The service layer correctly delegated the database operation. | Gokcen | 2025-07-23 | verify(leaderboardRepository, times(1)).upsertScore... | Pass | Confirms the service logic for adding a new score.
4. Avatar Endpoints
Test Case ID | Test Name & Number | Test Steps | Expected Results | Actual Results | Who Carried Out The Test | When | Logs/Assertions | Status | Notes/Explanations
AVAT-C-001 | Get Avatars by GameType Endpoint | 1. Mock AvatarService.<br>2. Perform a GET request to /api/avatars with a gameType parameter. | The endpoint must return HTTP 200 OK. The avatarService.findAvatarByGameType method must be called. | As expected. The controller successfully handled the request and called the service. | Gokcen | 2025-07-23 | verify(avatarService, times(1)).findAvatar... | Pass | Confirms the avatar retrieval endpoint is working.
AVAT-S-001 | Get Avatars Service Logic | 1. Mock AvatarRepository to return a list of avatars.<br>2. Call avatarService.findAvatarByGameType(). | The service should return the exact list of Avatar entities provided by the repository. | As expected. The service correctly passed the data from the repository to the caller. | Gokcen | 2025-07-23 | assertEquals(2, result.size()) | Pass | Verifies the business logic for fetching avatars.